ŽMOGIŠKŲJŲ IŠTEKLIŲ VALDYMO STRATEGIJOS (HRS4R) DIEGIMAS LIETUVOS AGRARINIŲ IR MIŠKŲ MOKSLŲ CENTRE

Finansavimo sutarties Nr.10-040-T-0034

Projektas  finansuojamas Ekonomikos gaivinimo ir atsparumo didinimo plano „Naujos kartos Lietuva“ ir Lietuvos Respublikos valstybės biudžeto lėšom

2026

Akademija, Kėdainių raj.

Įvadas

Šiuo metu Viešojoje įstaigoje Lietuvos agrarinių ir miškų mokslų centre (toliau - LAMMC) dirba beveik 200 Žemės ūkio mokslų srities Agronomijos ir Miškotyros mokslo krypčių mokslininkų bei studijuoja 67 doktorantai. Pastaraisiais metais vis didesnis dėmesys yra skiriamas LAMMC tarptautiškumo stiprinimui. Įsijungus į įvairias tarptautines organizacijas (EPSO, ISHS, UFRO ir kt.) buvo ženkliai padidintas konkursas į doktorantūros studijas, ko pasėkoje net 25 proc. LAMMC doktorantų yra užsienio šalių universitetus baigę studentai. Didėjantis užsienio šalių studentų susidomėjimas doktorantūros studijomis rodo ne tik LAMMC žinomumą, bet ir patikimumą. Didesnis naujų studentų srautas padėjo sukurti palankią ekosistemą tarp disciplinų tyrimų plėtrai LAMMC. Nepaisant to, stebimas mažas aktyvumas mokslininkų konkursuose. Siekdami stiprinti tyrėjų pasitikėjimą LAMMC bei užtikrinti patrauklias darbo sąlygas tiek šalies, tiek užsienio mokslininkams, siekiantiems pradėti ar tęsti savo mokslinę karjerą LAMMC, priėmėme sprendimą dėl stiprinti tyrėjų karjeros patrauklumą įgyvendinant EMTE instrumentus (diegiant žmogiškųjų išteklių valdymo strategiją (HRS4R), tyrėjų karjeros stebėsenos sistemą ir kt.) (EMTE veiksmas Nr. 4: Skatinti patrauklią ir tvarią mokslinių tyrimų srities karjerą, subalansuotą talentų apykaitą ir tarptautinį, tarpdisciplininį ir tarpsektorinį judumą visoje EMTE). Projektu bus sprendžiamos problemos: mažas mokslininkų karjeros patrauklumas, mažas mokslininkų tarptautiškumas, lyderių trūkumas bei kt.

Žmogiškųjų išteklių strategija mokslininkams (HRS4R) yra Europos mokslininkų chartijos ir dėl Mokslininkų priėmimo į darbą elgesio kodekso (Charter & Code) įgyvendinimo priemonė. Suprasdami, kad HRS4R yra ilgalaikis įsipareigojimas, apimantis bendras pastangas ir koordinavimą su įvairiomis vidaus ir išorės suinteresuotųjų šalių grupėmis, siekiame sėkmingai jam pasiruošti. Tikimės, kad sėkmingai įgyvendinus projektą bei įgyvendinus Chartijos ir kodekso principus LAMMC, institucija taps patrauklesnė mokslininkams, ieškantiems naujo darbdavio ar paskatins jau šiuo metu dirbančius LAMMC mokslininkus aktyviau dalyvauti projektuose.

Projekto tikslas buvo - stiprinti tyrėjų karjeros patrauklumą įgyvendinant EMTE instrumentus (diegiant žmogiškųjų išteklių valdymo strategiją (HRS4R), tyrėjų karjeros stebėsenos sistemą ir kt.) LAMMC.

HRS4R strategijos įgyvendinimas vyko pasitelkiant konsultantus bei aktyviai įtraukiant LAMMC žmogiškųjų išteklių specialistams bei kitiems administracijos darbuotojams, mokslininkams bei doktorantams.

Darbų atlikimo etapai:

1. EURAXESS registracija. LAMMC buvo užregistruotas EURAXESS, paskirtas HRS4R administratorius ir pateiktas įsipareigojimo laiškas.

2 Pirmą pusmetį buvo rengiami seminarai ir konsultacijos su vidinėmis ir išorinėmis suinteresuotosiomis šalimis strategijos kūrimui.

3. Buvo atlikta esamos būklės analizė ir išsamus LAMMC vertinimas pagal 40 Chartijos principus, identifituotos esamos stipriosios pusės ir trūkumai.

4. Atliktas įdarbinimo praktikos vertinimas, pabrėžiant atvirus, skaidrius ir nuopelnais pagrįstus procesus.

5. Suformuluotas veiksmų planas, pagrįstą spragų analize ir OTM-R kontroliniu sąrašu, apibrėžiant išmatuojamus veiksmus, pagrindinius veiklos rodiklius (KPI) ir terminus.

6. Pateikta paraiška  Europos Komisijai.

7. Parengtas priemonių planas HRS4R įgyvendinimui.

Atliktos projekto veiklos tiesiogiai paveiks visus LAMMC darbuotojus, kadangi Projektu bus sukurta nauja ir patraukli šalies ir užsienio mokslininkams darbo aplinka, grindžiama aiškumu, lygybės, atvirumo bei aukštais akademinės etikos reikalavimais.

Įgyvendinant projektą buvo atsižvelgiama į Jungtinių Tautų neįgaliųjų teisių konvencijos nuostatas. Projekto įgyvendinimo metu buvo laikomasi moterų ir vyrų lygybės ir nediskriminavimo dėl lyties, rasės, tautybės, kalbos, kilmės, socialinės padėties, tikėjimo, įsitikinimų ar pažiūrų, amžiaus, negalios, lytinės orientacijos, etninės priklausomybės, religijos, ir kt. principų. Projektas atitinka reikšmingos žalos nedarymo horizontaliuosius principus, yra tvarus aplinkos atžvilgiu ir vykdomas visapusiškai atsižvelgiant į Europos Sąjungos klimato ir aplinkos apsaugos standartus ir prioritetus. Projekto veiklomis prisidedama prie darnaus vystymosi ir lygių galimybių, įskaitant prieinamumo visiems įgyvendinimo. Projekte nebuvo vykdyti veiksmai, kurie galėtų riboti ar pažeisti Chartijoje numatytas pagrindines teises.

LAMMC darbuotojų apklauso rezultatai

An internal survey was carried out to understand how LAMMC’s community perceives the principles of the European Charter for Researchers in daily work. Its purpose was to identify the current situation and define a solid starting point for developing an Action Plan coherent with the Charter, enhancing what already works well and guiding improvement over the next three years. The questionnaire followed the four areas of the Charter — ethical and professional aspects, recruitment and selection, working conditions and social security, and training and development — and combined closed and open questions to collect both quantitative data and personal reflections. Ninety-four people took part, representing all researcher levels (R1–R4) and providing a balanced view of the institution. The analysis focused on identifying main trends and key messages emerging from staff experiences, offering a clear and honest picture of where LAMMC stands today and how it can continue to grow. Key Numbers at a Glance. To complement the qualitative analysis, the following key figures illustrate how LAMMC staff perceive the institution’s alignment with the principles of the European Charter for Researchers. These data offer a concise picture of awareness, fairness, autonomy, and institutional culture. This survey gave voice to many researchers and staff members across LAMMC, providing a rich and honest picture of how people experience their daily work, their supervisors, and their institution. Beyond the numbers, the responses tell a story of commitment, professionalism, and hope for clearer structures and stronger recognition. After reading results LAMMC appears as a mature and well-functioning organization, with a culture rooted in respect, freedom of research, and collaboration. At the same time, the answers reveal fragmentation: good practices exist, but they are not yet equally applied or communicated throughout the institution. The four pillars of the European Charter for Researchers provide a meaningful framework to understand these findings and identify areas for growth.

Participation numbers:

•	94 respondents across all researcher levels: R1 (34%), R2 (21%), R3 (28%), R4 (17%)

•	55% are early-career researchers — a balanced and representative sample.

Awareness and Ethics:

•	25% are fully aware of the HRS4R process and the Charter; 50% are not aware.

•	55% feel safe reporting ethical issues; 36% know where to seek advice on ethics.

•	44% are aware of the Gender Equality Plan and Policy.

Equality and Inclusion:

•	83% believe resources, training, and leadership opportunities are equally accessible.

•	62% perceive equal employment opportunities.

•	71% agree that recruitment and promotion are free from discrimination.

Academic Freedom and Working Environment:

•	86% feel free to choose their research topics and methods.

•	72% have autonomy in choosing conferences or internships.

•	57% maintain a healthy work–life balance.

•	65% integrate sustainability considerations into daily work.

Open Science and Research Assessment:

•	68% feel encouraged to apply open science principles.

•	41% have access to FAIR-data training.

•	60% consider infrastructure for open science sufficient.

•	64% believe their scientific results are assessed fairly, valuing quality as well as quantity.

Career Development and Recognition:

•	73% find career opportunities clearly communicated.

•	48% feel their work is properly appreciated.

•	41% understand the remuneration and incentive system.

•	40% receive sufficient performance feedback to plan career development.

Training, Mentoring, and Supervision:

•	55% have access to training opportunities appropriate for their career stage.

•	46% believe training and professional development are valued.

•	62% have access to a supportive supervisor.

•	51% say senior researchers actively support the career development of junior colleagues.

•	48% consider doctoral students to receive sufficient guidance.

Institutional Culture and Collaboration:

•	78% confirm that occupational health and safety rules are clearly communicated.

•	85% have received safety training.

•	44% believe there is an effective system for complaints and conflict resolution.

•	63% are encouraged to participate in joint activities or projects.

•	50% have opportunities to present or apply research results to society.

1. Ethical and Professional Aspects. LAMMC’s researchers express a strong sense of professionalism and respect for ethical standards. However, awareness of the institutional frameworks supporting these principles—such as the HRS4R process itself, the European Charter for Researchers, or the ethics procedures—is still limited. Many participants are unsure where to find information or whom to contact for advice on ethical issues. Similarly, while the majority feel that the workplace is safe and respectful, not everyone is fully confident about reporting mechanisms in case of inappropriate behavior or ethical violations. This does not indicate mistrust; rather, it points to a gap between values and visibility. Ethical principles are embraced, but the structures that sustain them remain in the background. A number of respondents also mention that institutional communication could be clearer—particularly about equality, gender balance, and diversity policies. In general, the ethical culture at LAMMC is healthy and positive, but it would benefit from stronger internal visibility, more transparent communication, and a sense that these policies are “alive” and relevant in daily practice rather than formal requirements.

2. Recruitment and Selection. The survey results show a good level of trust in the fairness of recruitment and promotion processes. Most respondents agree that LAMMC applies non-discriminatory practices and offers equal employment opportunities. Nevertheless, many comments highlight the need for more transparency and clarity in job advertisements, selection criteria, and career development pathways. Respondents often perceive that information about vacancies or advancement opportunities is not communicated early or widely enough. Similarly, while evaluation processes are generally considered fair, several participants express concern that assessments focus too much on quantitative indicators (such as publication counts) rather than on the quality, diversity, or societal impact of research results. The picture that emerges is one of principled fairness but uneven communication. Equality and merit are valued, but procedures are not always as transparent or comprehensible as staff would like. There is also a recurring feeling that professional growth depends more on personal initiative and the attitude of supervisors than on clear institutional rules.

3. Working Conditions and Social Security. This is one of LAMMC’s strongest pillars. Researchers and staff report a high degree of freedom and autonomy in their scientific work—freedom to choose topics, methods, and collaborations. This academic independence is one of the institution’s defining strengths. At the same time, people express concerns about workload, recognition, and balance. While many manage to maintain a healthy work–life equilibrium, others describe administrative overload, lack of clarity in remuneration systems, and limited formal recognition for contributions that go beyond research—such as teamwork, teaching, or outreach. Health and safety conditions are widely considered solid, and most respondents confirm they have received adequate training. Still, a few call for better communication and more practical refreshers to keep everyone updated. Another important theme relates to open science and infrastructure. Respondents are aware of the importance of FAIR data and open access, but many point to missing tools, insufficient training, or limited institutional support for data management. The willingness to engage with open science is clearly th ere; what is missing are consistent structures, resources, and technical guidance. Finally, collaboration and societal engagement emerge as defining aspirations. Researchers express genuine interest in participating in conferences, joint projects, and dissemination activities, but they often feel financially or administratively constrained. Many suggest that LAMMC could do more to encourage mobility and visibility, both nationally and internationally, and to make dissemination to society a recognized and supported part of research activity.

4. Training and Development. The responses related to training, feedback, and supervision reveal a mixed picture. LAMMC hosts many dedicated and supportive supervisors who encourage their staff’s professional development, and around two-thirds of respondents describe positive mentoring relationships. However, a substantial minority experience inconsistent or limited support. Some employees and doctoral students mention that meetings with supervisors are irregular or too task-oriented, leaving little space for long-term guidance or feedback. Others feel that senior researchers are approachable but too busy to offer regular mentoring. Across several responses, there is a shared wish for more structured mentoring, clearer feedback, and recognition of effort. Younger researchers in particular would like more opportunities to learn from experienced colleagues, to be included in project teams, and to receive advice on career progression. Doctoral students express similar needs: they appreciate their supervisors but often lack institutional structures—such as formal progress reviews, training programs, or dedicated consultation hours—that could support their path more effectively. Despite these challenges, the motivation to grow, learn, and contribute is very strong. Staff members value training opportunities and professional development, yet many feel that such activities are not sufficiently recognized or rewarded within the institution. The potential for building a stronger learning culture is already there; what is needed is coherence and formal acknowledgment.

Mitigation and Improvement Actions. The following priorities emerge naturally from the survey results and can be structured around the four pillars of the European Charter for Researchers. These measures can be selected as possible actions for the Action Plan:

1. Ethical and Professional Aspects

•	Strengthen internal communication about HRS4R, ethics procedures, and reporting channels through accessible materials and dedicated contact persons.

•	Develop a visible, trustworthy structure for ethical guidance and conflict resolution.

•	Reinforce the visibility and implementation of the Gender Equality Plan.

•	Organize regular awareness sessions on integrity, equality, and research ethics.

2. Recruitment and Selection

•	Make job advertisements and evaluation criteria more transparent and accessible to all potential applicants.

•	Communicate selection timelines and procedures in a consistent way across departments.

•	Broaden evaluation frameworks to include qualitative aspects of research, teaching, collaboration, and societal impact.

•	Ensure that opportunities for advancement are clearly communicated and based on transparent rules.

3. Working Conditions and Social Security

•	Conduct regular workload analyses to ensure fair distribution and avoid overload.

•	Clarify remuneration and incentive systems, ensuring consistency and transparency.

•	Invest in open science infrastructure, repositories, and FAIR data training.

•	Establish mobility and dissemination funds to support participation in conferences and joint projects.

•	Promote a culture of recognition and appreciation in everyday practice.

4. Training and Development

•	Introduce a formal mentoring and supervision framework for early-career researchers and doctoral candidates.

•	Offer leadership training for supervisors.

•	Create guidelines with information on paths to guide professional growth and feedback discussions.

•	Recognize training and mentoring as integral parts of performance evaluation.

•	Facilitate structured feedback sessions and regular supervisor–staff meetings.

HRS4R veiksmų planas 2026-2028 m.

| Action 1 – Ethics & Research Integrity Framework | - Charter principles: 1, 15 - Gap addressed: Limited visibility of procedures; lack of clear contact points - Action: Establish an Ethics & Integrity Framework including an Ethics Helpdesk, clear procedures, and confidential reporting mechanisms - Responsible units:, HR Department - Timeline: Q2 2026 – framework design and consolidation; Q3 2026 – approval and designation of contact points; Q4 2026 – awareness session and operational launch. - Indicator: Framework approved; Helpdesk operational; awareness session delivered annually |
| --- | --- |
|  | Remarks: Consolidate existing fragmented guidance into one institutional “Ethics & Integrity” page (English + local language). Appoint a designated contact point (part-time role) and define an escalation path (informal advice → formal report). Introduce an anonymous/confidential reporting channel (e.g., a secure webform managed by HR/Legal/IT with clear data protection notes). Deliver one annual awareness session embedded in induction and refreshed for supervisors. Keep the framework lightweight by using standard templates and a short SOP (2–3 pages). |
| Action 2 – Communication on Academic Freedom and Research Autonomy | - Charter principles: 2 - Gap addressed: Partial awareness of autonomy rights and limitations - Action: Develop and implement annual communication and information activities on academic freedom - Responsible units: Research and Innovation department - Timeline: Q3 2026 – first communication package and briefing; Q4 2027 and Q4 2028 – annual refresh and briefing. - Indicator: Communication materials published; annual briefing organised |
|  | Remarks: Publish a one-page “Research Autonomy & Responsibilities” note clarifying rights, responsibilities, and typical constraints (funders, contracts, supervision). Hold a short yearly briefing (online or hybrid) with Q&A, prioritising early-career researchers. Include a section in project kick-off checklists to ensure autonomy constraints are discussed transparently. Use simple communication assets (FAQ, intranet post, onboarding slide) to minimise workload. |
| Action 3 – Open Science Starter Package | - Charter principles: 3, 9, 17 - Gap addressed: Limited Open Science support and training; lack of DMP guidance - Action: Adopt an Open Science policy, provide DMP templates, designate Open Science contacts, and organise annual FAIR training - Responsible units: Research and Innovation department - Timeline: Q3 2026 – policy and DMP templates; Q4 2026 – designation of contacts and first FAIR training; Q4 2027 and Q4 2028 – annual training and updates. - Indicator: Policy approved; training delivered annually; number of researchers trained |
|  | Remarks: Adopt an institutional Open Science policy (short, principle-based) covering publications, data, and responsible sharing. Provide a Data Management Plan (DMP) template aligned with common funder requirements and a short “how-to” note. Nominate an Open Science contact per division (no new FTE) to route questions and share good practices. Deliver one annual FAIR/Open Science training (can be delivered via external providers or shared materials). If a repository is not feasible immediately, define an interim solution (trusted external repositories) and a roadmap. |
| Action 4 – Sustainability and Green Research Practices | - Charter principles: 8 - Gap addressed: Lack of structured sustainability practices - Action: Develop a Sustainability Policy and Green Research Guidelines - Responsible units: Research and innovation department - Timeline: Q4 2026 – draft policy and guidelines; Q1 2027 – approval and dissemination; Q4 2027 – first review of practices. - Indicator: Policy approved; guidelines disseminated |
|  | Remarks: Publish a short Sustainability Policy defining priorities (energy, materials, procurement, travel) and researcher-friendly practices. Develop “Green Research/Green Lab” guidelines with a checklist approach (do’s/don’ts) rather than complex audits. Include sustainability prompts in project planning (e.g., travel justification, data storage choices). Identify 2–3 quick wins per year (e.g., default virtual meetings, green procurement options, lab waste reduction). |
| Action 5 – Qualitative Research Assessment Framework | - Charter principles: 6, 9, 17 - Gap addressed: Over-reliance on quantitative metrics - Action: Develop qualitative assessment rubrics aligned with responsible research assessment principles - Responsible units: HR Department - Timeline: Q4 2026 – draft qualitative rubrics; Q2 2027 – pilot implementation; Q4 2027 – assessor training and adoption. - Indicator: Framework adopted; assessors trained |
|  | Remarks: Develop simple qualitative rubrics that recognise a broad set of contributions (Open Science, mentoring, leadership, collaboration, societal impact). Pilot the rubrics in one or two assessment processes before scaling. Provide assessor guidance to reduce bias (short training + calibration session). Ensure transparency by publishing criteria and examples of evidence (portfolio approach). |
| Action 6 – OTM-R Light Recruitment Workflow | - Charter principles: 10, 11 - Gap addressed: Inconsistent recruitment practices - Action: Standardise job advertisements, selection procedures, and systematic use of EURAXESS - Responsible units: HR Department - Timeline: Q2 2026 – workflow and templates; Q3 2026 – implementation and EURAXESS alignment. - Indicator: Standard templates adopted; EURAXESS usage monitored |
|  | Remarks: Introduce a single recruitment workflow with minimum mandatory steps: approval, advertising, selection, offer. Standardise job ads to include role, tasks, selection criteria, working conditions, and career development opportunities. Require EURAXESS publication for eligible posts and maintain a small log (dates, links). Provide a checklist to hiring managers to ensure consistent documentation |
| Action 7 – Transparent Selection Criteria and Feedback | - Charter principles: 10, 11 - Gap addressed: Limited transparency and inconsistent feedback - Action: Publish selection criteria in advance and introduce structured feedback for candidates - Responsible units: HR Department - Timeline: Q4 2026 – feedback templates and guidance; Q1 2027 – implementation; Q4 2027 and Q4 2028 – monitoring and refinement. - Indicator: Feedback templates used; candidate satisfaction monitored |
|  | Remarks: Publish selection criteria and scoring rubric before applications close. Introduce a standard feedback template covering strengths, development areas, and next steps. Provide a minimum service standard (e.g., feedback available upon request for shortlisted candidates). Train committee chairs on consistent communication and non-discrimination |
| Action 8 – Simplified R1–R4 Career Framework | - Charter principles: 12 - Gap addressed: Lack of clarity on career progression - Action: Map existing roles to R1–R4 profiles and communicate progression pathways - Responsible units: HR - Timeline: Q3 2027 – mapping and drafting; Q3 2027 – consultation; Q4 2027 – publication and communication. - Indicator: Career framework published and disseminated |
|  | Remarks: Map current job families/roles to R1–R4 and define typical expectations, skills, and evidence per level. Translate and summarise national qualification requirements in accessible language (including English). Create a “Career Pathway Map” visual and integrate it into onboarding and annual reviews. Ensure the framework is guidance-based (non-binding) to remain compatible with national rules. |
| Action 9 – Researcher Mobility Support Guidelines | - Charter principles: 7, 12, 19 - Gap addressed: Limited mobility support - Action: Develop practical guidelines and administrative support for mobility - Responsible units: Research and Innovation department - Timeline: Q3 2027 – guidelines and administrative setup; Q4 2027 – operational support and communication. - Indicator: Guidelines published; number of mobility cases supported |
|  | Remarks: Publish mobility guidance: eligibility, funding sources, administrative steps, and timelines. Provide a central administrative contact to support inbound/outbound mobility cases. Where feasible, establish a small mobility support mechanism (e.g., priority travel support; co-funding for strategic cases). Recognise mobility as positive evidence in relevant evaluations (linked to Action 5). |
| Action 10 – Transparency on Salaries, Workload, and Contracts | - Charter principles: 4, 5, 13, 14, 15 - Gap addressed: Limited clarity on employment conditions - Action: Provide clear guidance on salary rules, workload expectations, and contract timelines - Responsible units: HR - Timeline: Q3 2026 – guidance documents; Q4 2026 – first Q&A session; Q4 2027 and Q4 2028 – annual updates. - Indicator: Guidance documents published; annual Q&A sessions held |
|  | Remarks: Produce an accessible salary and benefits guide explaining rules, components, and whom to contact. Introduce a simple workload monitoring approach (e.g., annual pulse survey + discussion at management level). Clarify renewal timelines and communicate predictable decision points within the legal framework. Reduce administrative burden by standardising templates and offering short “how-to” sessions for researchers. |
| Action 11 – Complaint and Ombudsperson Pathway | - Charter principles: 15 - Gap addressed: Limited effectiveness of complaint mechanisms - Action: Define and communicate a clear complaint pathway and designate an ombudsperson - Responsible units: HR - Timeline: Q2 2026 – pathway design; Q3 2026 – designation and publication. - Indicator: Pathway published; ombudsperson appointed |
|  | Remarks: Define a clear pathway for concerns (workplace issues, harassment, conflicts, ethics), including confidentiality guarantees. Designate an ombudsperson function (can rotate, part-time) with clear scope and boundaries. Publish a short guide describing steps, timelines, and protection from retaliation. Align with existing national/legal obligations and data protection requirements |
| Action 12 – Dissemination and Exploitation Support | - Charter principles: 16 - Gap addressed: Limited institutional support for dissemination - Action: Develop dissemination guidelines and basic institutional support mechanisms - Responsible units: Communication Department - Timeline: Q3 2027 – dissemination toolkit; Q4 2027 – support mechanisms operational; Q4 2028 – review. - Indicator: Guidelines adopted; number of supported activities |
|  | Remarks : Produce a dissemination toolkit: templates, branding guidance, open access guidance, and a basic dissemination plan template. Create a light-touch internal review/support step for major outputs (press releases, policy briefs). Maintain a calendar of opportunities (events, calls for policy engagement) and highlight success stories. Encourage researchers to document dissemination evidence for portfolios (linked to Action 5). |
| Action 13 – Institutional Mentoring Programme | - Charter principles: 18, 20 - Gap addressed: Lack of structured mentoring - Action: Introduce a voluntary mentoring programme with clear guidelines - Responsible units: HR Department - Timeline: Q2 2027 – programme design; Q3 2027 – pilot launch; Q4 2028 – evaluation and consolidation. - Indicator: Number of mentor–mentee pairs; participant feedback |
|  | Remarks: Launch a pilot mentoring cycle for early-career researchers with clear roles and expectations. Provide a short mentor guide and optional training for supervisors/mentors. Offer structured milestones (kick-off, mid-point check, closing review) with minimal administrative overhead. Monitor quality through anonymous feedback and adjust annually |
| Action 14 – Training and Career Development Catalogue | Charter principles: 18, 19 Gap addressed: Fragmented access to training Action: Develop a central training catalogue focusing on career development and transversal skills Responsible units: HR Department Timeline: Q3 2026 – first catalogue; Q4 2026 – initial delivery; Q4 2027 and Q4 2028 – annual updates. Indicator: Catalogue published; participation rates |
|  | Remarks: Create a single training catalogue consolidating existing and external offerings (grant writing, leadership, supervision, Open Science). Set a minimum annual offer (e.g., 4–6 sessions/year) and prioritise high-impact skills for career progression. Where budgets are limited, use cost-effective formats (peer learning, shared materials, partner trainings). Track participation and perceived usefulness to refine the catalogue. |